## Street
| AS OF | 2023-03-17 |  |  |  | 2024 | 2025 | Total
[5 empty] | Conveyance | 161318327.88 | 224305391.12 | 385623719
[5 empty] | Sewer | 139370583.71 | 118020558.9 | 257391142.61
[5 empty] | GSI | 44896331.74 | 73349930.0075 | 118246261.7475
[5 empty] | Collectors | 184266915.45 | 191370488.9075 | 375637404.3575
[5 empty] | Count | 113 | 96 | 209
ProjectAutoID | Work No | Project Title | Project Type | Funding Source | Project Phase | Project Status | Targeted Bid FY | Project Estimate | Water Estimate | Sewer Estimate | GSI Estimate | Non-PWD Funding
5873 | 40736 | Flood Relief in Master St / Germantown Ave | Location-based | PWD Capital,BRIC | Projects Control | In PC | 2024 | 30578825 | 2821325 | 27058830 | 698670
7232 | 50257 | Black Coyle McBride Rain Garden | Location-based | PWD Capital | Projects Control | Funding Initiated | 2024 | 235797 | 0 | 0 | 235797
7522 | 41136 | Germantown SFR - N 21ST ST from STENTON TO GODFREY | Location-based | PWD Capital,BRIC | Projects Control | In PC | 2024 | 8559336 | 2315875 | 6243461 | 0
7739 | 50346 | 3rd & Norris Playground | Location-based | PWD Capital | Design | 70% Design | 2024 | 365094.25 | 0 | 0 | 365094.25
7302 | 50270 | Glenwood Green Acres | Location-based | PWD Capital | Design | Final | 2024 | 692322 | 0 | 0 | 692322
7695 | 41159 | Navy Yard Force Main P603 to P796 Replacement Phase 2 | Location-based | PWD Capital | Design | 50% Design | 2024 | 729600 | 0 | 729600 | 0
5989 | 40777 | Juniata Golf Course Dam Removal | Location-based | PWD Capital | Design | 90% Design | 2024 | 762340 | 0 | 762340 | 0
7205 | 50253 | Ridge Avenue Gateways | Location-based | PWD Capital | Design | 90% Design | 2024 | 897500 | 190000 | 347600 | 359900
6468 | 40926 | Amber / Braddock / Helen / Joyce | Location-based | Pennvest | Projects Control | In PC | 2024 | 6360248 | 2214626 | 4145622 | 0
7328 | 50276 | Craig Decatur | Location-based | PWD Capital | Design | Final | 2024 | 933698.11 | 119000 | 0 | 814698.11
7305 | 41102 | Clarion / Iseminger / Juniper / 11th | Location-based | Pennvest | Projects Control | In PC | 2024 | 6149324 | 2147511 | 4001813 | 0
5328 | 20545 | Cobbs Creek Pky / Springfield | Location-based | PWD Capital | Design | 50% Design | 2024 | 1000133.835 | 685250 | 0 | 314883.835
6598 | 50139 | Passyunk Avenue Medians Improvement | Location-based | PWD Capital | Design | 90% Design | 2024 | 1220000.13 | 0 | 0 | 1220000.13
7301 | 20611 | 49TH / BOTANIC / 51ST / GRAYS | Location-based | PWD Capital | Design | 70% Design | 2024 | 1234000 | 1234000 | 0 | 0
7135 | 50240 | Morris Park Neighborhood Streets 2 | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1315455 | 0 | 0 | 1315455
7174 | 41079 | Cantrell / Daly / Jackson / Winton / 8th | Location-based | Pennvest | Projects Control | In PC | 2024 | 6693115 | 2972337 | 3720778 | 0
5865 | 40850 | Ionic St. / Sansom / Ludlow | Location-based | PWD Capital | Design | 70% Design | 2024 | 1331950 | 581650 | 750300 | 0
6940 | 20573 | Tioga / Mercer / Salmon | Location-based | PWD Capital | Design | 90% Design | 2024 | 1363268.3175 | 1290000 | 0 | 73268.3175
7517 | 50310 | Wynnefield Ave Corridor | Location-based | PWD Capital | Design | 50% Design | 2024 | 1386782 | 0 | 0 | 1386782
7194 | 50248 | 61st and Grays Ave Streets Improvements | Location-based | PWD Capital | Design | 90% Design | 2024 | 1395763 | 0 | 0 | 1395763
7404 | 50287 | Lindbergh Blvd Traffic Triangles | Location-based | PWD Capital | Design | 70% Design | 2024 | 1396621 | 0 | 0 | 1396621
7371 | 41114 | Hoffman / Dudley / Mifflin / 4th / 5th / McKean | Location-based | Pennvest | Projects Control | In PC | 2024 | 5557237 | 2260738 | 3296499 | 0
6877 | 20559 | B /Cambria / Somerset | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1397670 | 1231462 | 9090 | 157118
7719 | 50341 | 62nd St from Webster St to Osage Ave | Location-based | PWD Capital | Design | 50% Design | 2024 | 1479094 | 0 | 0 | 1479094
6184 | 40923 | Mascher/Mutter/Palmer/Wilt | Location-based | PWD Capital | Design | 70% Design | 2024 | 1499150.01 | 704650 | 794500 | 0.01
6303 | 40864 | Alden / Media | Location-based | PWD Capital | Design | 50% Design | 2024 | 1542750 | 462500 | 1080250 | 0
6610 | 50141 | Loudoun Green Streets Improvements | Location-based | PWD Capital | Design | 70% Design | 2024 | 1582196.7425 | 0 | 118620 | 1463576.7425
7387 | 41118 | Belmar / Beaumont / Florence / Litchfield | Location-based | Pennvest | Projects Control | In PC | 2024 | 5206715.1 | 2050082.4 | 3156632.7 | 0
5424 | 20472 | Oxford St.,25th - 30th etal | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1585204.75 | 1489559.75 | 0 | 95645
5685 | 40980 | Kimball / 7th / Montrose | Location-based | PWD Capital | Design | 90% Design | 2024 | 1641250 | 800750 | 840500 | 0
7268 | 20606 | Springfield / Willow Grove | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1701496.2 | 1701496.2 | 0 | 0
5998 | 41064 | Ruffner / Blabon / Donath | Location-based | PWD Capital | Design | 70% Design | 2024 | 1709953.74 | 609625 | 1015750 | 84578.74
7502 | 41133 | Pine / Addison / Larchwood / Irving | Location-based | Pennvest | Projects Control | In PC | 2024 | 4849442 | 1881962 | 2967480 | 0
7697 | 50332 | Harbison Ave Streets 1 | Location-based | PWD Capital | Design | 50% Design | 2024 | 1761943.5075 | 352000 | 0 | 1409943.5075
6073 | 40987 | Broomall/Malcolm/56th etal | Location-based | Pennvest | Projects Control | In PC | 2024 | 5080057 | 2173303 | 2906754 | 0
7730 | 50342 | Overbrook Package | Location-based | PWD Capital | Design | 50% Design | 2024 | 1907038 | 0 | 0 | 1907038
7228 | 20596 | Diamond / Norris / 7th / Franklin | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1909507.5 | 1909507.5 | 0 | 0
6321 | 40907 | Etting / Napa / Corlies / Marston | Location-based | Pennvest | Projects Control | In PC | 2024 | 4368076 | 1683284 | 2684792 | 0
5668 | 20565 | Edison / Grant / Leon | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1941765 | 1941765 | 0 | 0
6767 | 20560 | 11th / 13th / Federal / Reed | Location-based | PWD Capital,Streets Department | Projects Control | Funding Initiated | 2024 | 1950653.6 | 1853653.6 | 0 | 0 | 97000
6309 | 40981 | Fitzgerald / American / Daly | Location-based | Pennvest | Projects Control | In PC | 2024 | 4166734 | 1547794 | 2618940 | 0
6887 | 20562 | Ellsworth / 21st / Morris | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1959213 | 1649477 | 0 | 309736
6661 | 41012 | 8th / Franklin | Location-based | Pennvest | Projects Control | In PC | 2024 | 3898887.33 | 1310044.33 | 2588843 | 0
7578 | 50322 | Hunting Park Cool Cover 3 | Location-based | PWD Capital | Design | 50% Design | 2024 | 1975249.1925 | 665275 | 0 | 1309974.1925
7217 | 20595 | Randolph / Franklin / Oxford / 9th | Location-based | PWD Capital | Projects Control | In PC | 2024 | 1979585.1 | 1979585.1 | 0 | 0
7236 | 20599 | Iseminger/ Camac / Shunk / 12th | Location-based | PWD Capital | Design | 90% Design | 2024 | 2005664.56 | 1785000 | 0 | 220664.56
6371 | 40896 | Clarion / Kater / Rodman | Location-based | PWD Capital | Design | 50% Design | 2024 | 2018150 | 840050 | 1178100 | 0
7248 | 20602 | Cambria / Glenwood | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2032485 | 2032485 | 0 | 0
7276 | 20607 | Cecil B Moore / Berks / 13th / Norris | Location-based | PWD Capital | Design | 70% Design | 2024 | 2044000 | 2044000 | 0 | 0
6060 | 20479 | Airdrie/L/Sedgley/Steinber/Bennington/K | Location-based | PWD Capital | Design | 50% Design | 2024 | 2048248.0225 | 1172200 | 0 | 876048.0225
5737 | 40780 | Harmer/Jefferson/Oxford/Yewdall/Hunter/56th/Lancaster | Location-based | PWD Capital | Design | 50% Design | 2024 | 2063534.74 | 535960 | 1184875 | 342699.74
6035 | 20578 | Magee / Erdrick / Gilham | Location-based | PWD Capital | Design | 90% Design | 2024 | 2078913.54 | 1955000 | 0 | 123913.54
7266 | 41097 | Front / 3rd / Cypress | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2088219 | 846104 | 1242115 | 0
7381 | 50284 | Erdrick Walker | Location-based | PWD Capital | Design | 90% Design | 2024 | 2106879 | 0 | 0 | 2106879
7242 | 20601 | Diamond / Page / 29th | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2113149 | 1940001 | 0 | 173148
5584 | 20487 | 29th / Reed / 30th / Moore | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2128353 | 1830020 | 0 | 298333
6292 | 40860 | 16th / 17th / Wharton | Location-based | PWD Capital | Design | 90% Design | 2024 | 2196317.7675 | 798000 | 1321200 | 77117.7675
7157 | 20588 | Godfrey / Park / Camac / Warnock / 10th | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2198657 | 1904374 | 0 | 294283
6293 | 40857 | Carlisle / 15th | Location-based | Pennvest | Projects Control | In PC | 2024 | 3449614 | 1307822 | 2141792 | 0
7673 | 50327 | Mount Airy Ave Green Streets | Location-based | PWD Capital | Design | 90% Design | 2024 | 2219479 | 233750 | 0 | 1985729
6203 | 20530 | Jefferson / Thompson / 5th | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2281455 | 2281455 | 0 | 0
6108 | 20546 | Ardleigh/Jane/Godfrey/Woodlawn | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2325573 | 2058400 | 0 | 267173
7790 | 50352 | Tarken Streets 1 | Location-based | PWD Capital | Design | 50% Design | 2024 | 2342415.7525 | 656550 | 0 | 1685865.7525
7014 | 50227 | Pennypack Creek Corridor Improvement Project at Holme Avenue | Location-based | PWD Capital | Design | 90% Design | 2024 | 2372156.84 | 0 | 0 | 2372156.84
5736 | 40882 | Auburn / Hagert / Rush / William | Location-based | PWD Capital | Design | 50% Design | 2024 | 2390950 | 1022500 | 1368450 | 0
5750 | 20558 | Sprague / Vernon | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2391051 | 2270525 | 0 | 120526
6542 | 40933 | Atlantic / Estaugh / 20th / 21st | Location-based | PWD Capital | Design | 90% Design | 2024 | 2416641.0625 | 760550 | 1403100 | 252991.0625
7252 | 20604 | Rutland/Horrocks/Lynford | Location-based | PWD Capital | Design | 50% Design | 2024 | 2425960.1775 | 2264000 | 0 | 161960.1775
7322 | 20614 | Elmwood / Buist / Chelwynde / Dicks / Este / 75th / 76th / 77th | Location-based | PWD Capital | Design | 70% Design | 2024 | 2427493.35 | 2237250 | 0 | 190243.35
7244 | 50259 | Cottman Ave (Castor to Blvd) | Location-based | PWD Capital | Design | 50% Design | 2024 | 2438703.6225 | 376000 | 0 | 2062703.6225
6914 | 41031 | Butler / Pike / Lawrence | Location-based | Pennvest | Projects Control | In PC | 2024 | 2944512 | 1069826 | 1874686 | 0
7458 | 41127 | Fontain / 16th / Cleveland / Gratz | Location-based | Pennvest | Projects Control | In PC | 2024 | 3491163 | 1622806 | 1868357 | 0
5639 | 40975 | Berks, Norris, 31st | Location-based | PWD Capital | Design | 90% Design | 2024 | 2439538.475 | 839000 | 1510100 | 90438.475
7143 | 41077 | Brandywine / 19th / 23rd / Pennsylvania | Location-based | Pennvest | Projects Control | In PC | 2024 | 4343115 | 2485405 | 1857710 | 0
5676 | 40775 | Kinsey / Cloud | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2490065 | 1155100 | 1334965 | 0
6109 | 41070 | Nicholas / Judson / Turner | Location-based | PWD Capital | Design | 90% Design | 2024 | 2528975.2425 | 1187000 | 1111500 | 230475.2425
6202 | 41008 | Baring & 41st | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2538112 | 1309133 | 1133819 | 95160
7298 | 20609 | Loretto / Pratt / Bridge | Location-based | PWD Capital | Design | 90% Design | 2024 | 2615856.765 | 2362000 | 0 | 253856.765
7229 | 20597 | Belmont Ave from S Georges Hill to Lancaster | Location-based | PWD Capital | Design | 50% Design | 2024 | 2620182.165 | 2548111 | 0 | 72071.165
7427 | 20626 | Bells Mill / Germantown / Sunset | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2761956 | 2761956 | 0 | 0
7116 | 41075 | Shunk / Mildred / Darien / 9th / Hutchinson | Location-based | Pennvest | Projects Control | In PC | 2024 | 3650559 | 1908014 | 1742545 | 0
7126 | 41076 | Panama / Cypress | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2788622 | 1269986 | 1518636 | 0
6766 | 40999 | 18th / Federal | Location-based | PWD Capital | Design | 70% Design | 2024 | 2830980 | 1166000 | 1664980 | 0
5739 | 20485 | 48th / Osage | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2891184 | 2427091 | 0 | 464093
6400 | 40898 | Morris / 18th / McClellan | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2946745 | 1169450 | 1777295 | 0
6504 | 40925 | Bambrey / Hilton / Stillman / Toronto | Location-based | PWD Capital | Projects Control | In PC | 2024 | 2967205 | 1246055 | 1721150 | 0
6655 | 20521 | Wissahickon / Park Line | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3042901 | 3042901 | 0 | 0
7297 | 41101 | Green / Lawrence / Hancock | Location-based | PWD Capital | Design | 50% Design | 2024 | 3092775 | 1423375 | 1669400 | 0
7313 | 50274 | 55th and Springfield Ave | Location-based | PWD Capital | Design | 90% Design | 2024 | 3146768 | 0 | 0 | 3146768
7209 | 50254 | Benton Brook Sewer Protection and Stream Restoration | Location-based | PWD Capital | Design | 90% Design | 2024 | 3278915.02 | 0 | 1000000.01 | 2278915.01
7211 | 20594 | 65th / Walnut Park / Mascher / Cheltenham | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3307420 | 3307420 | 0 | 0
6852 | 41025 | Warnock / Randolph / 9th | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3318779 | 1097202 | 1768594 | 452983
6963 | 41040 | D-05 DWO Modification | Location-based | PWD Capital | Projects Control | Funding Initiated | 2024 | 3344430 | 0 | 3344430 | 0
7147 | 41078 | Alder / Fulton / Catharine / Fitzwater | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3366135 | 1456712 | 1909423 | 0
6029 | 20575 | 15th / 18th / Uber / Wagner | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3393934 | 2575833 | 0 | 818101
6874 | 41068 | Alden / Cecil / Frazier | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3404459 | 1339090 | 1971040 | 94329
7237 | 41093 | Latona / Manton / 8th / Reese / Wharton | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3421474 | 1562827 | 1858647 | 0
6189 | 41018 | 2nd / Hancock / Orianna | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3604469 | 1648664 | 1955805 | 0
6516 | 40951 | 41st / Pine / Chester | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3626994 | 1268724 | 2232597 | 125673
7115 | 41074 | Arizona / Nevada / Dauphin | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3631110 | 1638585 | 1992525 | 0
6925 | 20564 | Tabor Road | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3704510 | 2720382 | 0 | 984128
7317 | 20613 | Columbus Blvd., Morris to Porter | Location-based | PWD Capital | Design | 90% Design | 2024 | 3760000 | 3760000 | 0 | 0
7128 | 20583 | Forrest / Wadsworth | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3771167 | 3155134 | 0 | 616033
7267 | 41098 | Delancey / Alden / Cecil / Locust | Location-based | PWD Capital | Design | 90% Design | 2024 | 3811782.8125 | 1800000 | 1460000 | 551782.8125
6076 | 40908 | Hadfield/Pentridge/50th etal | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3856850 | 1484580 | 1912477 | 459793
6323 | 40985 | Arch / Ruby / Lindenwood | Location-based | PWD Capital | Projects Control | In PC | 2024 | 3958665 | 1485720 | 1948720 | 524225
6314 | 20517 | Bayard / Cheltenham / Gowen / Provident et al | Location-based | PWD Capital | Projects Control | In PC | 2024 | 4074820 | 3688091 | 0 | 386729
6977 | 41048 | Venango, Kensington - Frankford | Location-based | Pennvest | Projects Control | In PC | 2024 | 2174707 | 1008221 | 1166486 | 0
6733 | 20552 | Knorr / Disston | Location-based | PWD Capital | Projects Control | In PC | 2024 | 4098761 | 3087405 | 0 | 1011356
6898 | 20561 | 52nd, Parrish - Merion | Location-based | PWD Capital | Design | 70% Design | 2024 | 4166350 | 4166350 | 0 | 0
6692 | 40965 | Moore / McClellan / 22nd | Location-based | PWD Capital | Projects Control | In PC | 2024 | 4178012 | 1650915 | 2386070 | 141027
6260 | 20462 | Ridge Ave., Parker - Summit | Location-based | PWD Capital | Design | 70% Design | 2024 | 6441180 | 6441180 | 0 | 0
5911 | 40709 | Annual Lining FY24 | Location-based | PWD Capital | Design | 90% Design | 2024 | 10000000 | 0 | 10000000 | 0
6777 | 40988 | Waverly Street (Streets Department reconstruction) | Partner | PWD Capital | Design | 90% Design | 2025 | 117600 | 42400 | 75200 | 0
8059 | 20682 | FRANKFORD AVE & HUNTING PARK AVE (TLD 48-INCH POINT REPAIR) | Location-based | PWD Capital | Design | 30% Design | 2025 | 204000 | 204000 | 0 | 0
5944 | 40760 | Pennypack Creek / Roosevelt Dam Removal | Location-based | PWD Capital,Federal Agency | Design | 50% Design | 2025 | 250000 | 0 | 0 | 250000
7500 | 50306 | Green Tree Run Outfall Stabilization | Location-based | PWD Capital | Design | 50% Design | 2025 | 829875.2 | 0 | 0 | 829875.2
6663 | 20533 | Franklin / 7th / 10th | Location-based | PWD Capital | Design | 30% Design | 2025 | 1198955.635 | 1139500 | 0 | 59455.635
7575 | 50321 | Herbert Overington | Location-based | PWD Capital | Design | 50% Design | 2025 | 1311311.2025 | 680000 | 0 | 631311.2025
6746 | 40977 | Upper Creshiem Tunnel and Outlet Stabilization | Location-based | PWD Capital | Design | 50% Design | 2025 | 1662758.17 | 1000000.17 | 662758 | 0
7325 | 20615 | 32nd / Glenwood | Location-based | PWD Capital | Projects Control | In PC | 2025 | 1686522 | 1686522 | 0 | 0
6907 | 50206 | Drexel University Campus Green Streets Package | Location-based | PWD Capital | Projects Control | In PC | 2025 | 1756458 | 0 | 0 | 1756458
3198 | 40751 | Sewer Lining at Specific Locations | Location-based | PWD Capital | Design | 70% Design | 2025 | 1757925 | 90000 | 1667925 | 0
7370 | 20621 | 19th / Gratz / Nicholas / 21st / 16th / Sydenham | Location-based | PWD Capital,Streets Department | Projects Control | Funding Initiated | 2025 | 1768984.8 | 1739184.8 | 0 | 0 | 29800
7807 | 50353 | Tarken Streets 2 | Location-based | PWD Capital | Design | 70% Design | 2025 | 1811544 | 0 | 0 | 1811544
7152 | 50243 | 56th St Tree Canopy Enhancements | Location-based | PWD Capital | Design | 90% Design | 2025 | 1825360 | 0 | 0 | 1825360
7421 | 50288 | McMenamy Torresdale | Location-based | PWD Capital | Design | Final | 2025 | 1863613 | 0 | 0 | 1863613
7555 | 50317 | Northwood Park Streets | Location-based | PWD Capital | Projects Control | In PC | 2025 | 1893191 | 0 | 0 | 1893191
7487 | 20636 | Haverford / 63rd / Girard | Location-based | PWD Capital | Design | 50% Design | 2025 | 1896546.8875 | 1812000 | 0 | 84546.8875
6491 | 40956 | Backflow Prevention Structure on C-6, C-13, C-16, and C-18 | Location-based | PWD Capital | Design | 50% Design | 2025 | 1900000 | 0 | 1900000 | 0
7220 | 50255 | Cobbs Creek Trail Rain Gardens | Location-based | PWD Capital | Design | 90% Design | 2025 | 1904556.9925 | 0 | 0 | 1904556.9925
5453 | 40618 | Upper Frankford LL Collector/Tacony Intercepting Sewer Lining Phase 4 | Location-based | PWD Capital | Design | 90% Design | 2025 | 1930000 | 0 | 1930000 | 0
7356 | 41111 | Titan / Hancock / Wharton / Manton | Location-based | PWD Capital | Design | 90% Design | 2025 | 1938000 | 858000 | 1080000 | 0
7498 | 50304 | 54th St Greening | Location-based | PWD Capital | Design | 70% Design | 2025 | 1970018 | 0 | 0 | 1970018
7262 | 41095 | T-10 Rehabilitation Plan | Location-based | PWD Capital | Design | 50% Design | 2025 | 2000000 | 0 | 2000000 | 0
7504 | 20639 | Sprague / Johnson / Boyer / Pleasant | Location-based | PWD Capital | Design | 50% Design | 2025 | 2012334.9375 | 1848750 | 0 | 163584.9375
7536 | 50314 | Woodbine Ave | Location-based | PWD Capital | Design | 70% Design | 2025 | 2035960.8275 | 0 | 0 | 2035960.8275
7357 | 41112 | 19th / Hamilton /21st / 22nd / Wood | Location-based | PWD Capital | Design | 90% Design | 2025 | 2064000 | 532000 | 1532000 | 0
7516 | 50309 | Mayfair Streets | Location-based | PWD Capital | Design | 70% Design | 2025 | 2067150 | 0 | 0 | 2067150
7431 | 20627 | Unity / Penn / Griscom / Oakland | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2068993.9 | 2068993.9 | 0 | 0
7494 | 20638 | 34th / Haverford / Spring Garden | Location-based | PWD Capital | Design | 50% Design | 2025 | 2128750 | 2128750 | 0 | 0
7380 | 50283 | Olney Rec Center | Location-based | PWD Capital | Design | 70% Design | 2025 | 2152809 | 0 | 0 | 2152809
6330 | 40875 | Greenway / Island / Saybrook / Upland | Location-based | PWD Capital | Design | 50% Design | 2025 | 2225808.855 | 1058400 | 893000 | 274408.855
7569 | 50319 | 59th Street Green Streets | Location-based | PWD Capital | Design | 70% Design | 2025 | 2294654 | 0 | 0 | 2294654
7391 | 41120 | Wharton / Dickinson / Percy | Location-based | PWD Capital | Design | 50% Design | 2025 | 2329000 | 924000 | 1405000 | 0
7446 | 20628 | Drexel / Sherwood / Overbrook / 66th | Location-based | PWD Capital | Design | 90% Design | 2025 | 2346000 | 2346000 | 0 | 0
6426 | 50107 | Carroll Park Streets | Location-based | PWD Capital | Design | 90% Design | 2025 | 2380000.18 | 0 | 0 | 2380000.18
7442 | 50292 | 65th and Greenway | Location-based | PWD Capital | Design | 70% Design | 2025 | 2392523.2175 | 637500 | 0 | 1755023.2175
7114 | 41073 | Warnock / Hutchinson / Mildred / 8th / 9th | Location-based | PWD Capital | Design | 50% Design | 2025 | 2399200 | 944000 | 1455200 | 0
7680 | 50330 | Allegheny West Green Gables | Location-based | PWD Capital | Design | 70% Design | 2025 | 2452671 | 0 | 0 | 2452671
7247 | 50260 | Haddington Woods Rain Garden | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2545739 | 0 | 0 | 2545739
6915 | 41033 | Parkside / Viola | Location-based | PWD Capital | Design | 90% Design | 2025 | 2578668.76 | 1204000 | 997000 | 377668.76
7385 | 20622 | Upsal / Yerkes / Cliveden / Washington / Crittenden | Location-based | PWD Capital | Design | 50% Design | 2025 | 2627312.875 | 1666000 | 0 | 961312.875
7299 | 50269 | Holmesburg Rec Center LAD | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2637680 | 0 | 0 | 2637680
7524 | 20641 | Aramingo / Huntingdon | Location-based | PWD Capital | Design | 90% Design | 2025 | 2677500 | 2677500 | 0 | 0
7856 | 41179 | Allegheny West | Location-based | PWD Capital | Design | 30% Design | 2025 | 2697142.76 | 1186500 | 941600 | 569042.76
7471 | 20633 | Richmond St and Venango | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2712595 | 2712595 | 0 | 0
6520 | 50128 | Weinberg Park and Street Locations | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2717277 | 0 | 0 | 2717277
7462 | 20631 | Manayunk / Cotton / Roxborough / Fleming | Location-based | PWD Capital | Design | 30% Design | 2025 | 2756000 | 2756000 | 0 | 0
5285 | 20417 | Gillespie / Cottage / Ditman / Devereaux | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2771254.75 | 2346589.75 | 0 | 424665
7392 | 20624 | Ryers / Hasbrook / Shelmire / Cottman / Lawndale | Location-based | PWD Capital | Design | 70% Design | 2025 | 2822907.2525 | 2748000 | 0 | 74907.2525
6086 | 20474 | Benner/Lawndale/Levick/Palmetto | Location-based | PWD Capital | Projects Control | In PC | 2025 | 2927344 | 2119714 | 0 | 807630
7016 | 50228 | Mt. Moriah Streambank and Cobbs Creek Interceptor Stabilization | Location-based | PWD Capital | Design | 70% Design | 2025 | 3013663.4 | 0 | 1596179 | 1417484.4
7417 | 20625 | Homer/Musgrave/Carnation/Magnolia/Washington | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3091917 | 2937328 | 0 | 154589
7418 | 41122 | Bodine/Carpenter/Hall/Montrose | Location-based | PWD Capital | Design | 70% Design | 2025 | 3097326.8475 | 1196000 | 1765000 | 136326.8475
7486 | 41131 | Coral / Arcadia / Vici / Orchard | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3130162 | 976170 | 2144840 | 9152
7339 | 20618 | Bridge / Pratt / Kirkbride / Richmond | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3170449.4 | 3170449.4 | 0 | 0
6747 | 50176 | Girard Estates Green Streets Improvements | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3201417.6 | 516774.6 | 0 | 2684643
7503 | 41134 | Newkirk / Myrtlewood / Dover / Jefferson | Location-based | PWD Capital | Design | 50% Design | 2025 | 3290000 | 1530000 | 1760000 | 0
7430 | 41124 | Hope / Mascher / Palethorp / Rockland / Roosevelt / Loudon | Location-based | PWD Capital | Design | 50% Design | 2025 | 3304852.625 | 1003000 | 2145000 | 156852.625
7426 | 41123 | 23rd / Harold / Huntingdon / Oakdale | Location-based | PWD Capital | Design | 50% Design | 2025 | 3354000 | 1564000 | 1790000 | 0
7373 | 41116 | Wyalusing / 45th / Poplar / 46th | Location-based | PWD Capital | Design | 70% Design | 2025 | 3378510.5875 | 1323250 | 1590000 | 465260.5875
7372 | 41115 | Regent / Upland / Farragut / Trinity / 49th | Location-based | PWD Capital | Design | 50% Design | 2025 | 3404000 | 1139000 | 2265000 | 0
5454 | 40619 | Upper Frankford Creek LL Collector/Tacony Creek Interceptor Lining Phase 5 | Location-based | PWD Capital | Design | 90% Design | 2025 | 3473750 | 0 | 3473750 | 0
7718 | 50340 | Brous & Battersby Streets | Location-based | PWD Capital | Design | 70% Design | 2025 | 3504304 | 0 | 0 | 3504304
7043 | 41072 | Seltzer / Sterner / 27th | Location-based | PWD Capital | Design | 30% Design | 2025 | 3548820.35 | 1840000 | 1201500 | 507320.35
7472 | 50297 | Ditman Green Corridor | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3584538 | 0 | 78090 | 3506448
7870 | 41186 | Buckley Terrance SFR | Location-based | PWD Capital | Design | 90% Design | 2025 | 3597000 | 285000 | 3312000 | 0
7440 | 41126 | Walker/ Algard / Erdrick / Montague / Gillespie | Location-based | PWD Capital | Design | 70% Design | 2025 | 3601715.965 | 1258000 | 2257500 | 86215.965
7546 | 41139 | Abigail / Dreer/ Arizona / Hope | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3645411.4 | 1415781 | 2229630.4 | 0
7374 | 41117 | Walton / Pine / Hazel | Location-based | PWD Capital | Design | 70% Design | 2025 | 3743096.0725 | 1224000 | 2436000 | 83096.0725
7530 | 50313 | Leon Gables | Location-based | PWD Capital | Design | 70% Design | 2025 | 3839795 | 600000 | 1178200 | 2061595
6276 | 40852 | Markoe / Westminster / 46th | Location-based | PWD Capital | Projects Control | In PC | 2025 | 3906900 | 1466890 | 2440010 | 0
7816 | 41174 | Ogden & 48th Streets | Location-based | PWD Capital | Design | 30% Design | 2025 | 3924225 | 2412425 | 1511800 | 0
6269 | 40855 | Bott / Lycoming / Nice | Location-based | PWD Capital | Design | 50% Design | 2025 | 3944500 | 1295000 | 2649500 | 0
7439 | 41125 | 5th / York / Fairhill | Location-based | PWD Capital | Design | 70% Design | 2025 | 4080000 | 1190000 | 2890000 | 0
7007 | 50224 | Neill Drive Pumping Station Stream Restoration and Infrastructure Protection | Location-based | PWD Capital | Design | 70% Design | 2025 | 4085600 | 0 | 0 | 4085600
7338 | 41108 | Letterly / Gaul / York | Location-based | PWD Capital | Design | 70% Design | 2025 | 4191250 | 1326000 | 2865250 | 0
5677 | 40990 | 60th / Ludlow / Chestnut | Location-based | PWD Capital | Projects Control | In PC | 2025 | 4255068 | 2058045 | 1642245 | 554778
5878 | 41004 | 11th / Cambria area | Location-based | PWD Capital | Projects Control | In PC | 2025 | 4258781 | 1336370 | 2922411 | 0
7271 | 50263 | Rowland Leon | Location-based | PWD Capital | Projects Control | In PC | 2025 | 4371454 | 0 | 63080 | 4308374
7176 | 41081 | Venango, 6th - 9th / Marshall / Rising Sun | Location-based | PWD Capital | Projects Control | In PC | 2025 | 4388937 | 1214282 | 3174655 | 0
7326 | 41105 | Callowhill / 61st | Location-based | PWD Capital | Design | 90% Design | 2025 | 4401463.9575 | 1330000 | 2974500 | 96963.9575
6662 | 41002 | Alter / Ringgold / 27th | Location-based | PWD Capital | Design | 30% Design | 2025 | 4525050 | 1263000 | 3262050 | 0
7389 | 41119 | Wolf / Bouvier / Colorado / 18th | Location-based | PWD Capital | Design | 50% Design | 2025 | 4613000 | 1575000 | 3038000 | 0
7514 | 41135 | 26th / 27th / Arizona | Location-based | PWD Capital | Design | 90% Design | 2025 | 4799335.87 | 1999750 | 2396600 | 402985.87
7321 | 41103 | 48th / Walton / Cedar / Hazel | Location-based | PWD Capital | Design | 70% Design | 2025 | 4905972.3575 | 1574000 | 3131100 | 200872.3575
6893 | 41021 | Queen / Penn / Morris | Location-based | PWD Capital | Design | 90% Design | 2025 | 4918400 | 1195000 | 3723400 | 0
6561 | 40935 | Cross / Mountain / 4th | Location-based | PWD Capital | Projects Control | In PC | 2025 | 4978478 | 1805257 | 3173221 | 0
7202 | 41086 | York / Marston / 26th / Cumberland | Location-based | PWD Capital | Design | 50% Design | 2025 | 4993000 | 1513000 | 3480000 | 0
6066 | 40859 | Mayfield/Sheridan etal | Location-based | PWD Capital | Projects Control | In PC | 2025 | 5081718 | 1804565 | 3086803 | 190350
5969 | 20536 | Wyoming Ave. / Whitaker Ave. | Location-based | PWD Capital | Projects Control | In PC | 2025 | 5430446 | 4620580 | 0 | 809866
5447 | 40612 | Cobbs Creek Intercepting Sewer Lining Phase 2 | Location-based | PWD Capital | Projects Control | In PC | 2025 | 5495000 | 0 | 5495000 | 0
7756 | 41166 | Fairmount / Brown | Location-based | PWD Capital | Design | 50% Design | 2025 | 5603594.3925 | 1940400 | 3177750 | 485444.3925
7483 | 41130 | Columbia / Belgrade | Location-based | PWD Capital | Projects Control | In PC | 2025 | 5641424 | 1722262.5 | 3919161.5 | 0
7798 | 41172 | Carpenter / Quincy / Cresheim | Location-based | PWD Capital | Design | 30% Design | 2025 | 6227350 | 1715700 | 4511650 | 0
7708 | 41160 | HAVERFORD AVE, 56TH ST, 58TH ST | Location-based | PWD Capital | Design | 50% Design | 2025 | 6997000 | 2587000 | 4410000 | 0
6717 | 50169 | Grays Ferry Neighborhood GSI Stormsewer | Location-based | PWD Capital | Design | 90% Design | 2025 | 7178793 | 989500 | 320000 | 5869293
7984 | 20676 | Schuylkill River Crossing (SRX) Tunnel | Location-based | PWD Capital,WIFIA | Design | Transmitted to Design | 2025 | 121235712 | 121235712 | 0 | 0 |  | 126550025.01 | 141112686
[7 empty] | Total | 761387923.3575 | 385623719 | 257391142.61 | 118246261.7475 | 126800
Notes:
Funding Sources include planned BRIC and PENNVEST applications. Funding subject to approval from FEMA/PEMA and PENNVEST.

## Facility
| AS OF | 2023-03-17
|  |  |  | 2024 | 2025 | Total
|  |  | Facilities | 344929511.98 | 410069382.2 | 754998894.18
|  |  | Count | 67 | 42 | 109
ProjectAutoID | Work No | Project Title | Project Type | Funding Source | Project Phase | Project Status | Targeted Bid FY | Project Estimate
7269 | 60015 | Load Control SCADA Replacement | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 7500000
5631 | 61080 | Raw Water Basin Outlet Gates Addition | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 8000000
5910 | 61092 | Air/Water Surface Wash System Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 15000000
6032 | 61103 | Masonry Repairs and Window/Door Replacement | Plant and Facility | PWD Capital,PWD Operating | Design | Design Started | 2025 | 4000000
6166 | 61110 | New Process Lab Addition | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 2300000
6792 | 61125 | Filter Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 5000000
7050 | 61132 | Replacement of Filter Drains and Influent Valves | Plant and Facility | PWD Capital | Projects Control | In PC | 2024 | 21173440
7159 | 61133 | Sodium Hypo Tanks Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 2500000
7215 | 61136 | Process Lab Water Sampling Lines Replacements/Additions | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 1500000
7219 | 61138 | Baxter FWS Courts 1, 2, 3 Valve Replacements/Additions | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 4500000
7292 | 61139 | Pre/Applied Hydrated Lime Dosing Betterment | Plant and Facility | PWD Capital | Design | Transmitted to Design | 2024 | 1000000
7330 | 61140 | Admin/Filter/Pre/Post/Intake Buildings Roof Replacement | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 6000000
7465 | 61147 | Ferric Delivery System Betterment | Plant and Facility | PWD Capital | Design | 60% Design | 2024 | 250000
7481 | 61149 | Motor Control Centers Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1000000
7691 | 61154 | Carbon Storage Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 2482167.19
7722 | 61155 | Washwater Towers Industrial Coating/North Control Valve & Supply Piping Replacement | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 2200594.92
7997 | 61158 | Hydrated lime system dust control betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 300000
8037 | 61160 | FWB Roof Vents Replacement and Cleaning | Plant and Facility | PWD Capital,PWD Operating | Design | Design Started | 2025 | 10000000
6362 | 62129 | CFE Sluice Gates and RM Isolation Valves Betterment | Plant and Facility | PWD Capital | Projects Control | In PC | 2025 | 2911376
6789 | 62139 | Filter Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 4000000
6961 | 62144 | Filter Building Window Replacement | Plant and Facility | PWD Capital | Design | 60% Design | 2024 | 1700000
7212 | 62150 | Admin Bldg. Addition | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1500000
7282 | 62152 | Backwash Tower Betterment | Plant and Facility | PWD Capital | Design | 60% Design | 2024 | 2500000
7383 | 62156 | Sed Basin Clarifier Arm and Drive Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 6500000
7449 | 62158 | Control Lab Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1500000
7538 | 62159 | Replacement of the Lime Transfer System | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 425000
7561 | 62160 | Fluoride System Replacement | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 4000000
7690 | 62161 | Chemical Building Elevator and Crane Trolley Betterment | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 1310617.25
7785 | 62162 | Filter Backwash Valve Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1800000
7812 | 62163 | Maintenance Storage Building Replacement | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 1800000
7882 | 62167 | CHEMICAL BUILDING INTERIOR WORKSPACE BETTERMENT | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1600000
7930 | 62168 | REPLACEMENT OF FLOCCULATOR / CLARIFIER ELECTRICAL CONTROL EQUIPMENT | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 750000
7981 | 62169 | Monument Road Tank Replacement | Plant and Facility | PWD Capital,WIFIA | Design | Design Started | 2025 | 44409816
8027 | 62171 | Belmont WTP/Monument Road Yard Piping Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 19876000
8032 | 62172 | Filter & Chemical Building Piping Protective Coating Replacement Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1000000
5543 | 63061 | Butler Building (Arch) Addition - Storage Facility and Welding Shop | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 1100000
5544 | 63062 | Butler Building (Plumb) Addition | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 120000
5495 | 63063 | Butler Building (Elec) Addition | Plant and Facility | PWD Capital | Design | 95% Design | 2024 | 995000
5833 | 63077 | Hydrated Lime Storage and Feed System Addition | Plant and Facility | PWD Capital | Projects Control | In PC | 2025 | 3705000
5849 | 63079 | North Side Backwash Valves Replacement | Plant and Facility | PWD Capital | Projects Control | In PC | 2024 | 1477000
7154 | 63097 | Sodium Hypo Tank Replacement | Plant and Facility | PWD Capital | Design | 30% Design | 2024 | 3500000
7628 | 63100 | Hydrated Lime Storage and Feed System Addition Electrical) | Plant and Facility | PWD Capital | Projects Control | In PC | 2024 | 752560
7723 | 63101 | Queen Lane Valve and Electric Actuator Replacements | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 3126235.62
7758 | 63102 | Elevator Replacement and Structural Betterment at PTB | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 350000
7787 | 63104 | Central Court and Drainage Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1351953.73
7789 | 63106 | Roof and Plumbing System Betterments at the Filter Building and Chemical Maintenance Building | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 3977459.85
7802 | 63107 | North Clearwell Basin Roof Replacement and Structural and Mechanical Betterment | Plant and Facility | PWD Capital | Design | 30% Design | 2025 | 17000000
7815 | 63109 | Backwash Switchgear and Starters Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 5975000
7929 | 63110 | Queen Lane Mobile Pilot Plant Addition | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1600000
7959 | 63111 | Post Treatment Building Rehabilitation | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 301679
8085 | 63114 | Queen Lane WTP 36" Backwash Discharge Pipe and Valves Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 5000000
6409 | 64072 | 15KV Switchgear and Standby Generator @ QLRWPS Addition | Plant and Facility | PWD Capital,BRIC | Design | 60% Design | 2024 | 11000000
6658 | 64084 | East Park Booster Pumping Station Betterment - GEN | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2024 | 25649755
6695 | 64086 | Lardner's Point Pumping Station (Gen) Replacement | Plant and Facility | PWD Capital | Design | 30% Design | 2025 | 60000000
6775 | 64090 | Queen Lane Filtered Water Pumping Station Emergency Generator Addition | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 2500000
6951 | 64098 | Torresdale Raw Water PS Overhead Crane Replacement and Building Betterment | Plant and Facility | PWD Capital | Design | 95% Design | 2024 | 4600000
6952 | 64099 | Chestnut Hill Pump Station Betterment | Plant and Facility | PWD Capital | Design | 90% Design | 2025 | 8700000
7251 | 64109 | Belmont Raw Water PS Betterment | Plant and Facility | PWD Capital,PWD Operating | Design | Design Started | 2025 | 4500000
7277 | 64111 | George's Hill Pump Station Addition and Belmont High Pump, Motor, VFD Replacement | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2025 | 21743567
7537 | 64115 | Chesnut Hill PS Suction/Discharge Header Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 2000000
7818 | 64124 | Upper Rox Basins Industrial Coating Betterment | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 10000000
7820 | 64125 | Upper Rox Basins 1-4 Industrial Coating Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1250000
7823 | 64126 | Upper Rox Basins Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 7208743.04
7853 | 64127 | Roxborough fresh water storage tank corrosion systems replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 99879
7946 | 64130 | Schuylkill River Crossing Pumping Station Addition | Plant and Facility | PWD Capital,WIFIA | Design | Design Started | 2025 | 19876974
7957 | 64131 | Lardner's Point Pumping Station Site Preparation | Plant and Facility | PWD Capital | Design | 60% Design | 2024 | 60000000
8069 | 64132 | George's Hill Pump Station Addition and Belmont High Pump, Motor, VFD Replacement - Elec | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2025 | 6000000
8070 | 64133 | George's Hill Pump Station Addition and Belmont High Pump, Motor, VFD Replacement - HVAC | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2025 | 1000000
8071 | 64134 | George's Hill Pump Station Addition and Belmont High Pump, Motor, VFD Replacement - PLUM | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2025 | 1000000
8075 | 64135 | East Park Booster Pumping Station Betterment - ELEC | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2024 | 16000000
8076 | 64136 | East Park Booster Pumping Station Betterment - HVAC | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2024 | 1000000
8077 | 64137 | East Park Booster Pumping Station Betterment - PLUM | Plant and Facility | PWD Capital,WIFIA | Design | 30% Design | 2024 | 500000
5842 | 71097 | DAF Tank Collectors Flights and Chains Replacement | Plant and Facility | PWD Capital | Design | 60% Design | 2024 | 7000000
6790 | 71114 | Replacement of the Scum System at Northeast WPCP | Plant and Facility | PWD Capital | Design | 60% Design | 2024 | 20000000
7173 | 71119 | Laboratory Replacement (#2) | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1027000
7294 | 71122 | PTB, PST, and Digester Control Station Betterment | Plant and Facility | PWD Capital | Design | Transmitted to Design | 2025 | 6000000
7355 | 71124 | Polymer Dosing System Betterment | Plant and Facility | PWD Capital | Design | 30% Design | 2025 | 1500000
7424 | 71125 | Fuel Oil Tank Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1000000
7429 | 71126 | Plant Road Paving and Regrading Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 3200000
7451 | 71128 | Aeration System (Mechanical) Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 2670000
7452 | 71129 | Aeration System (Electrical / Instrumentation) Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1196000
7584 | 71130 | Existing PTB Building and Process improvements | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 1500000
7652 | 71138 | Betterment of Switchgear for Digesters | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1900000
7654 | 71139 | Process Tank Components Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 16000000
7655 | 71140 | Digester Piping Replacement | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 7000000
7656 | 71141 | Sludge Screening Facility Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 8000000
7805 | 71145 | Replacement of Aeration System Blowers | Plant and Facility | PWD Capital | Design | Transmitted to Design | 2025 | 9150000
7903 | 71147 | HVAC and Glycol System Betterment at the Sludge Gas Facilities | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 3000000
8049 | 71148 | Property for Plant Addition | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 7500000
8062 | 71149 | Fencing and Security Addition for New Property | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 3000000
5396 | 72070 | Scum Equipment (Gen) Betterment | Plant and Facility | PWD Capital | Design | 30% Design | 2025 | 6000000
5633 | 72071 | Scum Equipment (Elec) Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1100000
7468 | 72093 | Laboratory Replacement (#3) | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1500000
7956 | 72094 | Betterment of the Influent Pumping Station - 4160 Volt Switchgear and Motor Controls | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 5000000
5904 | 73065 | Final Sedimentation Tank Betterment | Plant and Facility | PWD Capital | Design | 30% Design | 2025 | 40000000
6798 | 73087 | Mixers at Aeration Tanks Replacement | Plant and Facility | PWD Capital | Design | 60% Design | 2025 | 32000000
7053 | 73089 | Process Air Piping and Blowers Replacement | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 25708189.86
7162 | 73090 | SW Lagoon Drainage Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 3000000
7183 | 73091 | Laboratory Replacement (#1) | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 8000000
7309 | 73095 | Oxygen Plant Cold Box Distillation Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 5000000
7735 | 73109 | Final Sedimentation Tank Return Sludge Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 3500000
7976 | 73118 | Process Air Piping and Blowers Replacement - HVAC | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 1438762.5
7977 | 73119 | Process Air Piping and Blowers Replacement - Electrical | Plant and Facility | PWD Capital | Design | 90% Design | 2024 | 4448570.22
1563 | 75028 | Linden Ave P.S. - Gen/Mech. Betterment | Plant and Facility | PWD Capital | Projects Control | In PC | 2024 | 1147554
1564 | 75029 | Linden Ave P.S. - Electrical Betterment | Plant and Facility | PWD Capital | Projects Control | In PC | 2024 | 263000
6586 | 75054 | Broad and Blvd Stormwater Pump Station Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 2000000
6588 | 75056 | Lockart Pump Station Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2024 | 1750000
6590 | 75058 | Milnor Street Pump Station Betterment | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 1750000
7752 | 80020 | BLS Online Water Quality Monitoring Building and Parking Lot Addition | Plant and Facility | PWD Capital | Design | Design Started | 2025 | 3500000
Total | [7 empty] | 754998894.18
Notes:
Funding Sources include planned BRIC and PENNVEST applications. Funding subject to approval from FEMA/PEMA and PENNVEST.